## PROPOSED TIMELINE
UR Student Proposed Cutover Approach - DRAFT/FOR DISCUSSION ONLY!!
UR Student Cutover Deadline or Key Activity
UR Standard Academic Calendar Item
| 2019-04-01 | 2019-04-02 | 2019-04-03 | 2019-04-04 | 2019-04-05 | 2019-04-06 | 2019-04-07 | 2019-04-08 | 2019-04-09 | 2019-04-10 | 2019-04-11 | 2019-04-12 | 2019-04-13 | 2019-04-14 | 2019-04-15 | 2019-04-16 | 2019-04-17 | 2019-04-18 | 2019-04-19 | 2019-04-20 | 2019-04-21 | … | [147 empty] | … | 2019-09-30 | 2019-10-01 | 2019-10-02 | 2019-10-03 | 2019-10-04 | 2019-10-05 | 2019-10-06 | time axis 2019-04-22 to 2019-09-15
| Day in the Life Testing (March - Mid April) | [13 empty] | Follow on Testing As Needed | [7 empty] | 2019-05-20: Daily Cutover "What You Can Do Today!!!" Communications to Key Offices
Student Setup Activity Post Go Live | [22 empty] | 2019-06-24: UR Financials Fiscal Year Close Activities; 2019-07-08: Students Setup ACH for Refunds (esp MD, FT Simon and MS)
Undergrads: Students complete Fin Resp Form, Payment Plans, Friends & Family via onboarding
[121 empty] | Grads: Students complete Fin Resp Form, Friends & Family via onboarding | [34 empty] | Grads: September 15 Bill Pay Plan Setup
Grads: August 15 Bill Pay Plan Setup
Dual Entry Periods | [22 empty] | 2019-05-20: TRACK FOR RE-ENTRY AFTER CUTOVER: New Instructors
[65 empty] | TRACK FOR RE-ENTRY AFTER CUTOVER: Fall 2018 Activity and Prior (registrations, changes of status, grading) | [34 empty] | DUAL ENTRY PERIOD FOR REGISTRATIONS (ADDs/DROPs) / CHANGE OF STATUS FOR SUMMER 2019 ACTIVITY
[91 empty] | TRACK FOR RE-ENTRY AFTER CUTOVER: New Non-Matrics, Changes in Status, Changes to Bio/Demo, Transfer Credit, Holds | [8 empty] | CATCH UP FOR ALL RE-ENTER ITEMS FROM PRIOR TO CUTOVER)
Academic Calendar(s) | SPRING 2019 | [21 empty] | 2019-05-20: FULL SUMMER 2019 TERM; 2019-08-19: Intl; 2019-08-21: UG Orientation; 2019-08-28: FALL 2019
[51 empty] | SUMMER A (4 WEEK TERM) | [41 empty] | SUMMER B (4 WEEK TERM)
[51 empty] | SUMMER A (6 WEEK TERM) | [41 empty] | SUMMER B (6 WEEK TERM)
[72 empty] | ESM Comprehensive Exams | [13 empty] | ESM Summer Session
SIMON SUMMER 2019 (includes returning students as well as First Year Summer Starts)
[13 empty] | Simon Executive MBA Program | [9 empty] | 2019-07-22: SIMON PRE-FALL FOR FIRST YEAR MS/MBA
[65 empty] | Simon BERN program at Rochester | [41 empty] | SMD PhD Early Starts (Fall Matrics / Hospital Rotation)
SMD Psychology Internship Program
ECMS Summer Term
[83 empty] | EIOH GME Residents Start | [10 empty] | EIOH OFP, PERIO, PROSTO, Saudia Arabian AEGD, ORTHO Starts | [30 empty] | EIOH Preceptors, Group #1 | [31 empty] | EIOH Preceptors, Group #2
SMD Med Fall Term (3/4 year students)
Can we get this done in 1 week instead???
Activate UR Fin Configs for Student
Conversion Activities | [22 empty] | 2019-05-13: Update configs for Fall 2019 Dates; 2019-05-20: Pre-Course Configurations; 2019-06-08: Post Course Configurations; 2019-07-06: Post Section Config
CONFIGURATION SUPPORT | [22 empty] | 2019-05-20: Security / Initiation Only BPs; 2019-07-07: Update BPs with actual steps
Master Course Data | EXTRACT/TRANSFORM MASTER COURSE DATA | [21 empty] | 2019-06-03: LOAD/VALIDATE
Course Fees | [22 empty] | 2019-05-27: EXTRACT/TRANSFORM; 2019-06-03: LOAD/VALIDATE
CONVERT AHEAD DATA:
Convert Ahead Data - Institutions/Instructors | [22 empty] | 2019-05-20: Extract/Transform/Load Convert Ahead Data - Round 1
Update Universal ID in UR Financials for all Workers (and update integration)
Educational Institutions | [22 empty] | 2019-05-20: EXTRACT/TRANSFORM/LOAD ACTIVITY
Academic Affiliates/Appointments - Instructors
Instructor Eligibility
Convert Ahead Data - Fall 2018 Data and Prior | [22 empty] | 2019-06-10: Extract/Transform/Load Convert Ahead Data - Round 2
Student Bio/Demo Data - Run #1 | [22 empty] | 2019-06-10: EXTRACT/TRANSFORM/LOAD ACTIVITY
Student Matriculations - Fall 2018 and Prior
Course Sections - Fall 2018 and Prior
Program of Study History - can we split this into two?
Student Registrations - Fall 2018 and Prior
CUTOVER WEEK:
Transactional Data - Transcripts, Cohorts, Students, Matriculations, Comments, Manual Holds) | [22 empty] | 2019-06-29: Extract/Transform; 2019-07-05: Load
External Transcripts | [22 empty] | 2019-06-29: EXTRACT/ TRANSFORM; 2019-07-05: LOAD
Transfer Credit | bar: 2019-06-29 to 2019-07-06
Cohorts | bar: 2019-06-29 to 2019-07-06
Friends & Family | bar: 2019-06-29 to 2019-07-06
Catch Up Entry (manual) for any New Instructors for Summer 2019 (from activity entered by Academic Units since May 18) | bar: 2019-06-29 to 2019-07-06
Student Bio/Demo Data - Run #2 (Spring 2019 to current) | bar: 2019-06-29 to 2019-07-06
Student Matriculations - Spring/Summer/Fall 2019 | bar: 2019-06-29 to 2019-07-06
Student Comments - Stu Fin - right sequence? | bar: 2019-06-29 to 2019-07-06
Student Comments - Stu Records - right sequence? | bar: 2019-06-29 to 2019-07-06
Student Holds (MANUAL) | bar: 2019-06-29 to 2019-07-06
Last Minute Activity: Spring/Summer/Fall 2019 Sections, Registrations, POS History, Term Honors, Balance Forward | [22 empty] | 2019-07-05: Ext/Txr/Load
Course Sections - Spring/Summer/Fall 2019 | [22 empty] | 2019-07-05: EXTRACT/ TRANSFORM/LOAD
Program of Study History - can we split this into two? | bar: 2019-07-05 to 2019-07-07
Student Registrations - Spring/Summer/Fall 2019 | bar: 2019-07-05 to 2019-07-07
Term Honors/Academic Period Overrides | bar: 2019-07-05 to 2019-07-07
Completions (all, includes final program GPA) | bar: 2019-07-05 to 2019-07-07
Balance Forward Charges (confirm account balance holds placed automatically) | bar: 2019-07-05 to 2019-07-07
End of Summer Catchup Conversions
Student Finance Historical Transactions (@ end of 18-19 FA Aid year, filing of FISAP) | [172 empty] | ETL
POTENTIAL FOR DEFERRMENT:
Historical Students
Interfacing System Scheduled Upgrades:
PowerFaids (4x year) - includes August? (Parker)
Slate Upgrades (Kevin researching)
August 21st
- Financial Aid Disbursement for Fall 2019 can begin (7 days before Fall Term)
APRIL 1 - MASTER COURSE DATA FREEZE
- No further changes to Master Course Data (Course Catalog) until UR Student Go Live
Summer 2019 / Fall 2019 Online Registration Opens
MAY 31 - ANY ACTIVITY FOR FALL 2018 AND PRIOR ENTERS DUAL ENTRY PERIOD
- Activity against Fall 2018 and earlier (changes to sections, grades, student registrations, change of status) must be saved for dual entry into UR Student in July
UR Student Go/No Go Decision Point Option 2
JUNE 28 - NON-REGISTRATION DATA CUTOVER WINDOW BEGINS
- Dual Entry period for all but registration related-data for existing students (adds/drops)
- No addition of new students (non-matric)
- No changes of status, changes to POS after this date
- No changes to student bio/demo data-
- No posting of transfer credit
- No posting of manual student holds
- Admissions integrations pause until cutover
JULY 8 - UR STUDENT FIRST DAY IN PRODUCTION !!!
- Registration opens for Administrative Registration for all terms (NO ONLINE REGISTRATION FOR STUDENTS)
- Dual Entry for Summer Term activity begins (dual entry of all registration (add/drop) and change of status transactions for summer to support completing FA for 18-19 in ISIS). Manual adjustments to conversion account balance as needed by the Bursar's office to keep student in synch using existing Registration Activity reports.
- Auxiliary Charges can be posted to Fall 2019 (no auxiliary charges to be posted to Summer in UR Student)
- Admissions integrations re-instated, integrations to Blackboard and other campus based systems activated , including PowerFaids for AY19-20 (18-19 stays connected to ISIS)
- Integrations from UHS, Housing, Meal Plan and other systems with charges and payments for Fall
- Disbursements and Adjustments to Summer 2019 and prior term Financial Aid made in ISIS with balance corrections updated in UR Student by Bursar's office using Daily Activity Reports
- Grading for summer (and any term) can resume
- Adjustments for Prior Periods can resume
UR Student Go/No Go Decision Point Option 1
JULY 15 - Flat Rate Fee Assessment
- Fall 2019 Tuition & Fee Assessment - Flat Rate programs
- FA Fall 2019 Anticipated Aid must be loaded
- Simon/MD FA Disbursement (Date?)
JULY 19 - NSC Enrollment Reporting (Summer, Transmission #3) OUT OF ISIS
August 12 -
- NSC Enrollment Reporting (Summer, Final Transmission) - OUT OF ISIS
August 15 - Per Credit Hour Billing Begins for Fall 2019 - Group #1
Sept 15 - Per Credit Hour Billing Begins for Fall 2019 - Group #2
Commencement Weekend!
Summer Classes Start
MAY 20 - NEW INSTRUCTORS ENTER DUAL ENTRY
- Dual Enter Instructors for Summer Activity (hold for later entry into UR Student)
- Delay Entry of Instructors for Fall Activity
Summer B Classes Start
International Students
Move in Day - Domestic Students
Fall Classes Begin!
JULY 5 - REGISTRATION DEADLINE!!!
- All Registrations!!! ALL SCHOOLS / ALL PROGRAMS!!!
- All Grad Student Registrations for August Conferral Deadline!
- Final transmission of Bio/Demo and Enrollment integrations out of ISIS to campus-based systems
MAY 24 - DEADLINE!!! All Auxiliary Charges for Summer 2019 Revenue
- Summer Housing Charges
- Room Damage (any additional would be posted in July against Fall Revenue)
- Eastman Instrument Fees
- UROS Charges
- LIbrary Fines
- UHS Health Service Charges
Final ISIS Billing
Online Registration Deadline for Summer Term
Oct 1 - Dual Entry period ENDS for Summer activity
FA 18-19 year close out / filing of FISAP
Student Historical Financial Transactions brought into Workday
JULY 29 - Student Online Registration Opens
First Year Registration!!!
APRIL 15 - STUDENT/PARENT COMMUNICATIONS BEGIN
- Begin communicating upcoming changes for UR Student / actions required as they return to campus
(Duo, ACH setup, Onboarding)
July 1 - DUO Bulk Enrollment
Transfer Student Registration!!!

## BILLING GROUPS
July | August | September
AS&E FT Undergrads | AS&E Non-matric, UG and Grad | AS&E Grad students
AS&E PT Undergrads | EMBA students | Simon PhD students
ESM FT Undergrads | ECMS | Simon non-matric students
ESM PT Undergrads | ESM returning grad students | Warner students
Simon FT MBA students | ESM visiting students | TEAM students
Simon FT MS Students | Simon FT 2nd year MBA and MS students | Nursing per credit: FT, PT & non-matric
AS&E Study Abroad students | EIOH - all certificate programs | AS&E visiting students
AS&E Exchange students | MFT Masters students | SMD Masters students
Nursing FT APNN students | SMD PhD students | SMD non-matric students
All SMD Medical students